## Data
WEBSITE DEVELOPMENT (Start Date - 10 Nov 2025)
ID | TASK | START | DURATION | END | PREDECESSORS | MILESTONE | RESOURCE | RESOURCE TYPE | BASELINE START | BASELINE DURATION | BASELINE END
1 | Project Kickoff & Requirement Gathering | 2025-11-10 | 3 | 2025-11-12 |  | No | Team Lead | Work | 2025-11-10 | 3 | 2025-11-12
2 | Design (UI/UX) | 2025-11-13 | 5 | 2025-11-19 | 1 | No | Designer | Work | 2025-11-13 | 5 | 2025-11-17
3 | Setup Development Environment | 2025-11-13 | 2 | 2025-11-14 | 1 | No | DevOps | Work | 2025-11-13 | 2 | 2025-11-14
4 | Frontend Implementation | 2025-11-18 | 7 | 2025-11-26 | 2,3 | No | Frontend Dev | Work | 2025-11-18 | 7 | 2025-11-24
5 | Backend Implementation | 2025-11-18 | 7 | 2025-11-26 | 3 | No | Backend Dev | Work | 2025-11-18 | 7 | 2025-11-24
6 | Integration & Testing | 2025-11-25 | 5 | 2025-12-01 | 4,5 | No | QA Team | Work | 2025-11-25 | 5 | 2025-11-29
7 | User Acceptance Testing (UAT) | 2025-12-01 | 3 | 2025-12-03 | 6 | No | Client | Work | 2025-12-01 | 3 | 2025-12-03
8 | Project Handover (Milestone) | 2025-12-04 | 0 | 2025-12-03 | 7 | Yes | Team Lead | Work | 2025-12-04 | 0 | 2025-12-03
Formulas:
END = WORKDAY([START], [DURATION]-1)
BASELINE END = [BASELINE START] + [BASELINE DURATION] - 1